## Phases
Pingblender CPG Agent Package (MCP - A2A)
Client Name: | NewLCPG |  | Notes:
Graffiti : Secure AI Amplifiers | 2025-10-01 |  | Weekly project status call
Project End: | 2026-09-30 |  | Project Status Call when hours or milestone at 70%
Target Deadline | 2026-03-31 |  | Review project plan each week
Total Development Hours:
Phase I: RAG Data Identification & Preparation | Status | Owner | Estimated Completion Date | Notes
Phase I: List A - Requests (Each task must be completed to set status to complete) | Live | SynthetIQ | 2016-12-01
Task: Review of provided documentation and materials for requirements | Inactive | SynthetIQ/NewL
Task: Data Pulls and Comparison for each comparable metric architecture | Inactive | SynthetIQ/NewL
Task: Inventory of Data Point Congruencies and Non-Congruencies | Inactive | SynthetIQ
Task: Map 'Data Layer' Prototype to current business requirements | Inactive | SynthetIQ
Phase I: List B - Client Preparation | Inactive
Task: Provision access to a testing account and avail repository access to write/store | Dependency | NewL
Task: Provide access to version control | Dependency | NewL
Task: Provide access/communication to development cycle process owner | Dependency | NewL
Task: Target timeline for Prototype release and outline conditions for commit/deploy. | Dependency | SynthetIQ/NewL | 2016-12-23
Phase I: Close (Only upon completion/closure of List A/List B)
Phase II: Differentiated AI Agent Interfaces and Evaluating (DEV)
Phase II: List A - Code Snippet Collection, Construction, Local Emulation | Inactive
Task: Code snippet matrix creation and expanded SDR for GTM | Inactive | SynthetIQ
Task: Collision review, methods assessment and library inventory | Inactive | SynthetIQ
Task: Baseline code construction and emulation on localhost environment | Inactive | SynthetIQ
Task: Full pass localhost emulation with error-free functionality | Inactive | SynthetIQ
Phase II: List B - Dev/Testing Level Deployment | Inactive
Task: Apply skeleton application framework to SDK or Local Instance for demonstration | Inactive | SynthetIQ
Task: Internal review of functionality for points outlined in specification | Inactive | SynthetIQ
Task: Peer review and scrutiny of functionality prior to design pattern application | Inactive | SynthetIQ
Task: Bug list and feature request deadline reached. Outline final draft of production. | Inactive | SynthetIQ/NewL | 2025-11-15
Phase II: Close (Only upon completion/closure of List A/List B)
Phase III: A2A Deployment Testing & QA
Phase III: List A - Test Preparation (Each task must be completed to set status to complete) | Inactive
Task: Document method/expected outcome per requirements for each variable/event | Inactive | SynthetIQ/NewL
Task: Build a case matrix for each unique case including sequences and variations | Inactive | SynthetIQ/NewL
Task: Inventory of Data Point Congruencies and Non-Congruencies | Inactive | SynthetIQ
Task: Map 'Data Layer' Prototype to current business requirements | Inactive | SynthetIQ
Phase III: List B - Execution, Updates and Staging Deployment | Inactive
Task: Construct proposal and slides to illustrate data definition library. | Inactive | SynthetIQ
Task: Stakeholder discussion and presentation of proposal | Inactive | SynthetIQ
Task: Updates, Adaptation, and Follow Up | Inactive | SynthetIQ
Task: Client Sign-off | Inactive | SynthetIQ/NewL | 2025-12-15
Phase III: Close (Only upon completion/closure of List A/List B)
Phase IV:A2A Deployment Delivery (Warranty)
Phase IV: List A - Production Deployment | Inactive | SynthetIQ
Task: Code cycle close and update for documentation process | Inactive | SynthetIQ/NewL
Task: Emulation deployment review and scrutiny | Inactive | SynthetIQ/NewL
Task: Final bug list constructed and release notes update | Inactive | SynthetIQ
Task: Target release date and share timeline with NewL | Inactive | SynthetIQ
Phase IV: List B - NewL Preparation | Inactive
Task: Construct proposal and slides to illustrate data definition library. | Inactive | SynthetIQ
Task: Stakeholder discussion and presentation of proposal | Inactive | SynthetIQ
Task: Updates, Adaptation, and Follow Up | Inactive | SynthetIQ
Task: Knowledge Transfer of results to team, and NewL | Inactive | SynthetIQ/NewL | 2026-03-31
Phase IV: Close
Phase V: GTM Project Close (Final Release)
Phase V: List A - Outcomes Analysis and Feedback Closure | Inactive
Task: Regression testing cycles performed by internal objective third party | Inactive | SynthetIQ/NewL
Task: Code review and notes compilation for documentation update | Inactive | SynthetIQ/NewL
Task: Bug list rundown and closure of non-deployable tickets | Inactive | SynthetIQ
Task: Draft documentation guide and pairing with release level 1 release library | Inactive | SynthetIQ
Phase V: List B - Solution Documentation Finalization | Inactive
Task: Provide Brand a styling guide | Inactive | SynthetIQ
Task: Review living documentation from production review | Inactive | SynthetIQ
Task: Updates, Adaptation, and Follow Up | Inactive | SynthetIQ
Task: Sharing final document and release notes to NewL team | Inactive | SynthetIQ/NewL | 2026-09-30
Phase V: Close